## Sheet1
ISSUE ID | DATE REPORTED | REPORTED BY | S/N | DESCRIPTION | STATUS | COMMENTS | FURTHER CLARIFICATIONS BY CHH | NEW DATE SUBMITTED
|  |  | 1 | What is the relevance of the CUSTOMER INVOICE list? | NOT CLEAR |  | What we meant by the question is, why are the invoices stored up on that page? After they are processed, shouldn't they leave the page? | 13th December 2024
|  |  | 2 | CHANGE ACCOUNT PERIOD should have a dropdown of dates | NOT CLEAR | Not Required | The request is asking for a dropdown of months, instead of side scrolling to PREVIOUS & NEXT to the left or right. A dropdown is easier to choose from. | 13th December 2024
|  |  | 3 | What is the difference between ACCOUNT PAYABLE module & REQUISITION module? | NOT CLEAR | Payables is for your backlog while requisition is really time of process.
|  |  | 4 | What is the use of OTHER REVENUE REQUISITION module? | DROPPED | Dropped
|  |  | 5 | What is the use of RETURNS/EXCESS PAYMENT module? | DROPPED | Dropped
|  |  | 6 | What is unique about PETTY CASH/IMPREST module? | NOT CLEAR | Dropped
|  |  | 12 | In DISBURSEMENT/CHEQUE INSCRIPTION WRITING module, this page should be able to AUTO-GENERATE INSTRUCTION LETTER that will be sent to the Bank for transactions, with the system having already selected the accounts to be credited and debited. This is what Automation should be like. | NOT CLEAR |  | What we meant is that the software should be modeled in such a way that when a payment request is raised, it should end in the stage where the letter of instruction to be sent to Bank is auto-generated. One can select the transactions to be populated in the letter and print and send to the Bank. This features will minimise human error and aid the flow. | 13th December 2024
|  |  | 13 | In DISBURSEMENT/CHEQUE INSCRIPTION WRITING module, when you don’t select any BANK ACCTS and you hit PROCESS PAYMENT, the system still says ''PROCESSED SUCCESSFULLY''. THIS SHOULD NOT BE SO, because we didn't select any account to be credited. Please correct this. | NOT CLEAR |  | Did you test that module to know what we meant? You need to test it with a transaction (remember to delete the transaction from the system when you're done). | 13th December 2024
|  |  | 14 | In DISBURSEMENT/CHEQUE INSCRIPTION WRITING module, when you don’t select any BANK ACCTS and you hit PROCESS PAYMENT, the system still says ''PROCESSED SUCCESSFULLY''. THIS SHOULD NOT BE SO, because we didn't select any account to be credited. Please correct this. | NOT CLEAR |  | This enquiry should be clear. When an IOU is raised, there is usually a retirement that should follow afterwards, where the breakdown of what was spent is reported, and if there is any balance to be refunded, it is reported. How should this be treated on GIBS? This is urgently needed. | 13th December 2024
|  |  | 15 | There is a need to create a REJECT buttron at the Process Investment Journal Module, A REJECT will remove the transaction from the Process Investment Journal interface back to the Initiator (Asset Mgt - Investment Money) module for further action by the initiator. | NOT DONE |  | This is important if it can be effected. | 13th December 2024
4 | GROUP ACCOUNT - What is the plan for Group Account? |  | 19 | GROUP ACCOUNT - What is the plan for Group Account? | NOT DONE |  | Awaiting updates | 13th December 2024
|  |  | 20 | Under the Investment Interface, New Placement, upon attachment of supporting document, it doesn’t get attached after clicking on Add Document. | NOT DONE |  | Awaiting updates | 13th December 2024
| i. CAC certificate to be attached |  | 21 | i. CAC certificate should be among the docs to be attached | NOT CLEAR |  | This is to make the application smart and unique. Not one where anything goes. Such unique identifiers will help it to achieve that level of uniqueness. | 13th December 2024
| ii. RC Number to be provided, with a set format in the system, to avoid wrong inputs. |  | 22 | ii. RC Number to be provided, with a set format in the system, to avoid wrong inputs. | NOT CLEAR |  | This is to make the application smart and unique. Not one where anything goes. Such unique identifiers will help it to achieve that level of uniqueness. | 13th December 2024
|  |  | 23 | We should be able to add more BANKS to the available list of banks in the system. It should not be hard-coded. | NOT CLEAR |  | I think you have solved this by adding the list of Banks in several places inside the software | 13th December 2024
|  |  | 26 | Under Change Account Period, after selecting the account period and you save your data, nothing is displayed. It should display a notification that it has been successfully saved or not. | UNDER REVIEW |  | Awaiting updates | 13th December 2024
|  |  | 29 | 1. On the Investment Placement page, the FINANCIAL INSTITUTION should be changed to BENEFICIARY INSTITUTION. | 1. On the Investment Placement page, the FINANCIAL INSTITUTION should be changed to BENEFICIARY INSTITUTION. | 1. On the Investment Placement page, the FINANCIAL INSTITUTION should be changed to BENEFICIARY INSTITUTION. | 1. On the Investment Placement page, the FINANCIAL INSTITUTION should be changed to BENEFICIARY INSTITUTION. | 13th December 2024
|  |  | 30 | And the dropdown should contain all the banks in Nigeria. It currently has some of the Banks. | UNDER REVIEW |  | Awaiting updates | 13th December 2024
|  |  | 31 | 7. Under AGENCY CONTROL>CLIENT ADMINISTRATION>SECTOR, there is no option for FINANCIAL SERVICES. It should be included. | NOT DONE |  | Awaiting updates | 13th December 2024
|  |  | 32 | 11. Under AGENCY CONTROL>CLIENT ADMINISTRATION>NEW CLIENTS>SET CLIENT INFORMATION, ‘’. USE’’ should be edited to USER. | NOT CLEAR |  | This is simply a typographical error that should be corrected. | 13th December 2024
|  |  | 33 | 12. The CORPORATE CLIENT interface should be different from the PRIVATE INDIVIDUAL interface. | UNDER REVIEW |  | Awaiting updates | 13th December 2024
|  |  | 34 | PRIVATE INDIVIDUAL should have unique identifiers to avoid the same person appearing multiple times when the names are typed in differently. Unique identifiers like NIN & BVN. | UNDER REVIEW |  | Awaiting updates | 13th December 2024
|  |  | 35 | The CORPORATE entity's unique identifiers should be RC numbers & TIN, as no 2 companies can have the same RC & TIN numbers. | UNDER REVIEW |  | Awaiting updates | 13th December 2024
|  |  | 36 | 14. SEARCH BOX: Should include BVN/NIN for individuals, and RC/TIN for Corporate entities. | UNDER REVIEW |  | Awaiting updates | 13th December 2024
|  |  | 37 | 27. Under ASSET MGT>FIXED ASSET>NEW PURCHASE, QUANTITY should be automated depending on the Asset purchased, e.g. Building should be calculated by maybe in NUMBER OF ROOMS, LAND in SQUARE METRE, Vehicles/office Equipment/Furniture can be in UNITS. | UNDER REVIEW |  | Awaiting updates | 13th December 2024
|  |  | 38 | 28. PAID AMOUNT should also be automated after UNIT PRICE & QUANTITY have been filled. | UNDER REVIEW |  | Awaiting updates | 13th December 2024
|  |  | 39 | 29. ASSET TRANSFER is not working. | UNDER REVIEW |  | Awaiting updates | 13th December 2024
|  |  | 40 | 31. No Information under: DEPRECIATION VALUE, ASSET TRANSFER, NET BOOK VALUE. | UNDER REVIEW |  | Awaiting updates | 13th December 2024
|  |  | 7 | DISBURSEMENT module, what is it supposed to achieve? | DONE | Processing of payment
|  |  | 8 | In REQUISITION module, the PAYING BANK box should have a drop down of the list of All the Banks in Nigeria. | DONE | It Does
|  |  | 9 | In REQUISITION module, the RECEIVING BANK box should have a drop down of the list of All the Banks in Nigeria. We should NOT be manually typing names of Banks into these boxes. | DONE | Checked
|  |  | 10 | In REQUISITION module, BENEFICIARY box should have a list of PRE-REGISTERED VENDORS & THE NAMES OF ALL OUR STAFF because they are also beneficiaries. We should NOT be manually typing in names of beneficiaries, whether they're companies or individuals. | DONE
|  |  | 11 | In DISBURSEMENT/CHEQUE INSCRIPTION WRITING module, BANK ACCTS should have the list of ALL THE BANKS in Nigeria. | DONE |  | This is not so at our end. There are only two Banks there: Zenith Bank Plc & UBA Account.
1 | HR/PAYROLL module will be integrated into the application. |  | 16 | HR/PAYROLL module will be integrated into the application. | DONE
2 | BUDGETING module should be integrated/activated into the application |  | 17 | BUDGETING module should be integrated/activated into the application | DONE
3 | BANK RECONCILIATION module should be integrated into the application. |  | 18 | BANK RECONCILIATION module should be integrated into the application. | DONE
|  |  | 24 | The message that pops up when it logs you out shouldn’t be ACCESS DENIED. SESSION EXPIRED is better, to avoid confusion; because ‘’Access Denied’’ can mean many things; like ‘’you do not have access to a particular request’’ or ‘’Authorization needed for a particular process’’, etc. | DONE
|  |  | 25 | On the posting pages (Receivables, Payables, & Journal), the system should asterisk the compulsory fields that must be filled. | Done
|  |  | 27 | Under the Payables Interface, Vendors & Beneficiaries should be registrable. | DONE
|  |  | 28 | There should also be the option of registering new vendors with basic information like the Vendor’s company name, RC number, CAC doc, email, phone number, account details, contact person, etc. | DONE
|  |  | 41 | On the posting pages (Receivables, Payables, & Journal), the system should asterisk the compulsory fields that must be filled. | DONE
|  |  | 43 | Under the Payables Interface, Vendors should be registered. | DONE
12 | 2024-05-30 | Dan | 44 | LOG-OFF should not erase existing data there should be a buffer to retain data when logged back in. | DONE
11 | 2024-05-30 | Dan | 45 | LOG-OFF TIME without activity should be increased to 10 minutes. | DONE
| 2024-05-30 | Dan | 46 | ‘’Client Administration’’ should feed the GL posting automatically. | DONE
|  |  | 47 | This module, New Investment Placement, Monthly Accrued, the Cancel Button gives server error. The save button also gives server error. The backspace from the web browser url will return saved successfully and the data will now probably commit to the GL. Investigate. | DONE
|  |  | 48 | Similar to the observation raised earlier, New Investment Rollover, to ''Cancel'' goes into Server Error. | DONE
|  |  | 49 | This does not save. If you click cancel, it goes into Server Error. Please check the workings of the Investment Module generally. | DONE
|  |  | 50 | Button on Approve Items__ not working. | DONE
|  |  | 51 | Where a transaction has been approved by the Supervisor, an initiator can initiate an Auto Reverse subsequently, which will also have to go back to the Supoervisor to APPROVE of the Autoreverse action or REJECT as applicable. | DONE
6 | CUSTOMER INVOICE - DOWNLOADABLE INVOICES (so we can be able to download and share with clients. |  | 52 | Customer Invoices should be downloadable | DONE
| I. Other Revenue Requisition |  | 53 | In REQUISITION MODULE: Add the followings: Other Revenue Requisition, Expense Requisition, Returns/Excess Payments, Petty Cash (Imprest) | DONE
|  |  | 54 | Separate BONDS into CORPORATE BONDS & GOVT BONDS. | DONE
|  |  | 55 | Separate Placement into 90 DAYS & ABOVE 180 DAYS | DONE
|  |  | 56 | The tag DURATION (DAYS) should be removed. It is confusing since we have TENOR (DAYS) already. | DONE
|  |  | 57 | WOT, which stands for WITHHOLDING TAX, should be changed to WHT. | DONE
|  |  | 58 | Also, a PERCENTAGE SIGN (%) should be included in front of WHT. | DONE
|  |  | 59 | Under CUSTOMER INVOICES, all the terminologies that involve Insurance should be replaced with Investment terms. Insurance terms such as AGENCY CONTROL, AGENCY RECEIPT, INSURED NAME, BROKERS, PREMIUM, INSURED BROKERS, PREMIUM APPROVALS, DEBIT NOTES, CREDIT NOTES, etc. should be changed. | DONE
|  |  | 60 | Under REPORTS: The site goes back and displays an error. | DONE
|  |  | 61 | CLIENT ADMINISTRATION (Under AGENCY CONTROL) & ADMIN tab at the top: Why do they both exist separately and what is the difference? | DONE
|  |  | 62 | In Account Receivables, NAME OF BENEFICIARY should be changed to NAME OF PAYER | DONE
|  |  | 63 | In New Account Receivables, CHEQUE BANK NAME should have TRANSFER as the 1st option on the list. And on the other hand, if one should select CHEQUE, then the list of banks should then drop down for selection. | DONE
|  |  | 64 | CURRENCY: Across the posting pages, the NAIRA should be the default currency. Other currencies can be underneath for cases involving other currencies. But NAIRA should be the default | DONE
|  |  | 65 | Under the Investment Interface, when some fields have been left unfilled, it should display a notification of ‘’Incomplete data’’ and highlight the unfilled fields, rather than displaying ‘’Access Denied’’. | DONE
|  |  | 66 | VOUCHERS DELETION: JV24010900238/JV24010900249/JV24010900238/JV24010800230/JV24010900254/INV24010700008/JV24010900240/PV01240500108/JV24010900251/JV24010800215/JV24010800171/JV24010900252/JV24011000255/JV24010800172/PV01240500034/JV24010800113/JV24010800175. | DONE